## Sheet1
ITSC-3155 Software Engineering
Sprint 1 Backlog
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
Sprint 1 : 4/13 - 4/19
2.0 - Menu Management | 7 |  | 13 | 7.5 | 6 | 11 | 1 | 1 | 0 | To Do
Add CRUD router for sandwiches |  | Charlie | 3 | 5 | 3 | 0 | 0 | 0 | 0 | Done | 1
Add CRUD controller and router for Recipes |  | Ethan | 4 | 1 | 1 | 5 | 0 | 1 | 0 | Done | 1
Add CRUD controller and router for Resources |  | Ethan | 4 | 0.5 | 0 | 3 | 0 | 0 | 0 | Done | 1
Fix Payment schema/controller mismatch |  | Ethan | 2 | 1 | 2 | 3 | 1 | 0 | 0 | Done | 1
TOTAL |  |  | 13 | 7.5 | 6 | 11 | 1 | 1 | 0 |  | 14
Sprint 2 Backlog
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
1.1 - Menu Browsing | 5 |  | 2 | 3 | 0.5 | 0.5 | 0 | 0 | 0
Add category filter to GET /sandwiches |  | Charlie | 2 | 3 | 0.5 | 0.5 | 0 | 0 | 0 | Done | 2
8.1 - Reviews & Ratings | 5 |  | 2 | 6 | 0 | 0 | 0 | 0 | 0
Add GET /ratings/low endpoint |  | Charlie | 2 | 6 | 0 | 0 | 0 | 0 | 0 | Done | 2
7.0 - Chef Order View | 5 |  | 2 | 4 | 2 | 2 | 1 | 1 | 0
Add GET /resources/low endpoint |  | Ethan | 2 | 4 | 2 | 2 | 1 | 1 | 0 | Done | 2
9.1 - Promotions & Promo Codes | 5 |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 0
Add POST /orders/{order_id}/apply-promo |  | Ethan | 2 | 1 | 1 | 1 | 0.5 | 1 | 0 | Done | 2
6.0 - Staff Order View | 5 |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 0
Add date-range filtering to GET /orders |  | Ethan | 2 | 1 | 1 | 1 | 0.5 | 1 | 0 | Done | 2
10.0 - Data Analytics | 8 |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 0
Add GET /orders/revenue endpoint |  | Charlie | 2 | 1 | 1 | 1 | 0.5 | 1 | 0 | Done | 2
4.1 - Order Tracking | 3 |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 0
Add GET /orders/track/{tracking_number} |  | Charlie | 2 | 1 | 1 | 1 | 0.5 | 1 | 0 | Done | 2
11.0 - Documentation & Training | 6 |  | 2 | 1 | 1 | 1 | 0.5 | 1 | 0
Write one pytest unit test |  | Charlie | 2 | 1 | 1 | 1 | 0.5 | 1 | 0 | Done | 2
TOTAL |  |  | 16 | 18 | 7.5 | 7.5 | 3.5 | 6 | 0 |  | 14